## Sheet1
[8 empty] | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  |  | In Progress dates
| Project Start Date: | 2023-01-10 | [5 empty] | 2023-04-06 |  |  |  | 2024-04-16 |  |  |  | 2025-04-27 |  |  |  | 2026-04-30 |  |  |  | 2027-04-29 |  |  |  |  | Completion date
| Project Name | ORANGE ROTATOR CUFF INJURY MONITORING DEVICE |  |  |  | Week Starting |  | 2023-01-02 | 2023-04-06 | 2023-07-09 | 2023-10-11 | 2024-01-13 | 2024-04-16 | 2024-07-19 | 2024-10-21 | 2025-01-23 | 2025-04-27 | 2025-07-30 | 2025-10-28 | 2026-01-26 | 2026-04-30 | 2026-07-29 | 2026-10-31 | 2027-01-29 | 2027-04-29 | 2027-08-01 | 2027-10-30 | ♦ | Completed
# | Activity | Assigned To | Start | End | Days | Status | %Done
1 | Topic Selection & Design Brainstorming | Design Group | 2023-01-16 | 2023-02-06 | 16 | Complete | 100% | bar: 2023-01-02
2 | Preliminary Design & Report Summary | Design Group | 2023-02-08 | 2023-02-13 | 4 | Complete | 100% | bar: 2023-01-02
3 | Preliminary Presentation | Design Group | 2023-02-17 | 2023-02-27 | 7 | Complete | 100% | bar: 2023-01-02
4 | Refining Design | Design Group | 2023-02-27 | 2023-03-06 | 6 | Complete | 100% | bar: 2023-01-02
5 | Marketing & Leagal Considerations | Design Group | 2023-03-06 | 2023-03-13 | 6 | Complete | 100% | bar: 2023-01-02
6 | Prototype Demonstration | Design Group | 2023-03-13 | 2023-04-03 | 16 | Complete | 100% | bar: 2023-01-02 to 2023-04-06
7 | Project Plans & Advertisement | Design Group | 2023-04-03 | 2023-04-12 | 8 | In Progress | 80% | bar: 2023-04-06
8 | Recieve Feedback + Research + Improve Design | Design Group + Experts | 2023-04-12 |  |  | Not started | 0% | bar: 2023-04-06 to 2023-07-09
9 | Build Prototype 2 + New Prototype Presentation | Design + Testing Group | July |  |  | Not started | 0% | bar: 2023-07-09 to 2023-10-11
10 | Recieve Feedback + Research + Refine Design | Design Group + Experts | October |  |  | Not started | 0% | bar: 2023-10-11
11 | Build Prototype 3 + New Prototype Presentation | Design + Testing Group | October |  |  | Not started | 0% | bar: 2023-10-11 to 2024-01-13
12 | Receive Feedback + Research + Finalize Design | Design + Testing Group + Experts | January |  |  | Not started | 0% | bar: 2024-01-13
13 | Create & Present Finalized Product | Design + Manufarture Group | January |  |  | Not started | 0% | bar: 2024-01-13 to 2024-04-16
14 | Test & Present Calibration Validation Plan | Testing Group | January |  |  | Not started | 0% | bar: 2024-01-13 to 2024-04-16
15 | Product Presnentation (Product + User Manual) | Every member | April |  |  | Not started | 0% | bar: 2024-04-16
16 | Apply for liscence MDEL + IP/Brand Application | Sales & Marketing Group | April |  |  | Not started | 0% | bar: 2024-04-16 to 2024-10-21
17 | Manufacture Product | Manufacture Group | January |  |  | Not started | 0% | bar: 2025-01-23 to 2027-10-30
18 | Establish Retailers | Sales & Marketing Group | January |  |  | Not started | 0% | bar: 2025-01-23 to 2025-04-27
19 | Product Release | Sales & Marketing Group | July |  |  | Not started | 0% | bar: 2025-07-30
20 | Advertisement + Social Media Promotion | Sales & Marketing Group | January |  |  | Not started | 0% | bar: 2025-01-23 to 2026-04-30
21 | Finding Investors | Sales & Marketing Group | January |  |  | Not started | 0% | bar: 2025-01-23 to 2027-10-30
22 | Propose New Design/Improved Design | Design Group + Experts | April |  |  | Not started | 0% | bar: 2026-04-30 to 2026-07-29
23 | Preliminary Design & Report Summary | Design Group | July |  |  | Not started | 0% | bar: 2026-07-29
24 | Build new prototype + Demonstration | Design Group | October |  |  | Not started | 0% | bar: 2026-10-31 to 2027-01-29
25 | Find Investors for new project | Sales & Marketing Group | January |  |  | Not started | 0% | bar: 2027-01-29 to 2027-10-30
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
Statuses
Not started
In Progress
Blocked
Complete
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))